## Cover
TEST REPORT DOCUMENT
Project Name | Eatery Management System |  |  | Creator | LongCH
Project Code | EMS |  |  | Issue Date | 2024-02-23
Document Code | EMS Integration Test Report v2.0 |  |  | Version | 1.2
Record of change
Effective Date | Version | Change Item | *A,D,M | Change description | Reference
2024-02-23 | 1.0 |  | A | Create Integration test file.
2024-03-18 |  |  | M | Update Integration test.
2024-03-19 |  |  | M | Update Integration test.
2024-03-20 |  |  | M | Update Integration test.
2024-03-21 |  |  | M | Update Integration test.
2024-03-22 |  |  | M | Update Integration test.
2024-03-23 | 1.1 |  | M | Update Integration test.
2024-03-24 |  |  | M | Update Integration test.
2024-03-25 |  |  | M | Update Integration test.
2024-03-26 |  |  | M | Update Integration test.
2024-03-27 | 1.2 |  | M | Update Integration test.
2024-03-28 |  |  | M | Update Integration test.
2024-03-29 |  |  | M | Update Integration test.
2024-03-30 |  |  | M | Update Integration test.

## Test Cases
TEST CASE LIST
Project Name |  | Eatery Management System
Project Code |  | EMS
Test Environment Setup Description |  | 1. Server 2. My SQL 3. Web Browser
No | Function Name | Sheet Name | Description | Pre-Condition
1 | Login
2 | Logout
3 | View List Product
4 | Create product
5 | Update Product
6 | View Detail Product
7 | View List Category
8 | Create Category
9 | Update Category
10 | View Detail Category
11 | View List User
12 | Create User
13 | Update User
14 | View Detail User
15 | View List Table
16 | Create Table
17 | Update Table
18 | View Menu
19 | Add To Cart
20 | View Cart
21 | View List Order Dish
22 | View List Order
23 | View Order Detail
24 | View List Bill

## Test Statistics
TEST STATISTICS
Project Name | Eatery Management System |  | Creator |  | LongCH
Project Code | EMS |  | Reviewer/Approver |  | NAMLH
Document Code | EMS Integration Test Report v1.2 |  | Issue Date |  | 2024-02-23
Notes
No | Module code | Passed | Failed | Pending | N/A | Number of test cases
1 | Login | 6 | 0 | 0 | 0 | 6
2 | Logout | 3 | 0 | 0 | 0 | 3
3 | View List Product | 4 | 0 | 0 | 0 | 4
4 | Create product | 10 | 0 | 0 | 0 | 10
5 | Update Product | 9 | 0 | 0 | 0 | 9
6 | View Detail Product | 1 | 0 | 0 | 0 | 1
7 | View List Category | 4 | 0 | 0 | 0 | 4
8 | Create Category | 4 | 0 | 0 | 0 | 4
9 | Update Category | 4 | 0 | 0 | 0 | 4
10 | View Detail Category | 1 | 0 | 0 | 0 | 1
11 | View List User | 4 | 0 | 0 | 0 | 4
12 | Create User | 10 | 0 | 0 | 0 | 10
13 | Update User | 9 | 0 | 0 | 0 | 9
14 | View Detail User | 1 | 0 | 0 | 0 | 1
15 | View List Table | 3 | 0 | 0 | 0 | 3
16 | Create Table | 4 | 0 | 0 | 0 | 4
17 | Update Table | 4 | 0 | 0 | 0 | 4
18 | View Menu | 6 | 0 | 0 | 0 | 6
19 | Add To Cart | 3 | 0 | 0 | 0 | 3
20 | View Cart | 6 | 0 | 0 | 0 | 6
21 | View List Order Dish | 5 | 0 | 0 | 0 | 5
22 | View List Order | 3 | 0 | 0 | 0 | 3
23 | View Order Detail | 1 | 0 | 0 | 0 | 1
24 | View List Bill | 3 | 0 | 0 | 0 | 3
| Sub total | 108 | 0 | 0 | 0 | 108
| Test coverage |  | 100 | %
| Test successful coverage |  | 100 | %

## Login
Workflow | Login
Test requirement | Login
Number of TCs | 6
Testing Round | Passed | Failed | Pending | N/A
Round 1 | 6 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Login
LoginIT_1 | Test UI of login page. | 1. Navigate to Login screen. | 2. Login screen is display with "Tên đăng nhập", "Mật khẩu" and button "Đăng nhập". | Navigate to Login screen. | Failed | 2024-03-18 | LongCH | Passed | 2024-03-23 | LongCH | Passed | 2024-03-27 | LongCH
LoginIT_2 | Test login successful with role waiter. | 1. Enter input: + Tên đăng nhập : waiter. + Mật khẩu : 123456aA. 2. Click button "Đăng nhập" | 3. Navigate to screen of role waiter. | Navigate to Login screen. | Failed | 2024-03-18 | LongCH | Passed | 2024-03-23 | LongCH | Passed | 2024-03-27 | LongCH
LoginIT_3 | Test login successful with role manager. | 1. Enter input: + Tên đăng nhập : manager. + Mật khẩu : 123456aA. 2. Click button "Đăng nhập" | 3. Navigate to screen of role manager. | Navigate to Login screen. | Passed | 2024-03-18 | LongCH | Passed | 2024-03-23 | LongCH | Passed | 2024-03-27 | LongCH
LoginIT_4 | Test login with do not enter "Tên đăng nhập". | 1. Enter input: + Tên đăng nhập : + Mật khẩu : 123456aA. 2. Click button "Đăng nhập" | 3. The error message is display "Tên đăng nhập là bắt buộc" | Navigate to Login screen. | Failed | 2024-03-18 | LongCH | Passed | 2024-03-23 | LongCH | Passed | 2024-03-27 | LongCH
LoginIT_5 | Test login with do not enter "Mật khẩu". | 1. Enter input: + Tên đăng nhập : admin + Mật khẩu : 2. Click button "Đăng nhập" | 3. The error message is display "Mật khẩu chưa được nhập" | Navigate to Login screen. | Failed | 2024-03-18 | LongCH | Failed | 2024-03-23 | LongCH | Passed | 2024-03-27 | LongCH
LoginIT_6 | Test login with do not enter "Tên đăng nhập", "Mật khẩu". | 1. Enter input: + Tên đăng nhập : + Mật khẩu : 2. Click button "Đăng nhập" | 3. The error message is display "Tên đăng nhập là bắt buộc", "Mật khẩu chưa được nhập" . | Navigate to Login screen. | Passed | 2024-03-18 | LongCH | Passed | 2024-03-23 | LongCH | Passed | 2024-03-27 | LongCH

## Logout
Workflow | Logout
Test requirement | Logout
Number of TCs | 3
Testing Round | Passed | Failed | Pending | N/A
Round 1 | 3 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Login
LogoutIT_1 | Test logout with role waiter. | 1. Click button "Logout". | 2. Return to the login screen | Login in system with role waiter. | Passed | 2024-03-18 | LongCH | Passed | 2024-03-23 | LongCH | Passed | 2024-03-27 | LongCH
LogoutIT_2 | Test logout with role manager. | 1. Click button "Logout". | 2. Return to the login screen. | Login in system with role manager. | Passed | 2024-03-18 | LongCH | Passed | 2024-03-23 | LongCH | Passed | 2024-03-27 | LongCH
LogoutIT_3 | Test logout with role owner eatery. | 1. Click button "Logout". | 2. Return to the login screen. | Login in system with role owner eatery. | Failed | 2024-03-18 | LongCH | Failed | 2024-03-23 | LongCH | Passed | 2024-03-27 | LongCH

## View List Product
Feature | View List Product
Test requirement | View List Product
Number of TCs | 4
Testing Round | Passed | Failed | Pending | N/A
Round 1 | 4 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
View List Product
Product_1 | Test view list products. | 1. Click on "Sản phẩm" button on left-corner menu. | 1. Product list screen is displayed with fields "Số thứ tự", "Ảnh" , "Tên sản phẩm" , "Giá" , "Danh mục" , "Trạng thái" , "Quản lý". | Login with manager account or eatery owner. | Passed | 2024-03-18 | LongCH | Passed | 2024-03-23 | LongCH | 2024-03-27 | Passed | LongCH
Product_2 | Test view list products with paging. | 1.Click "<<" ">>" button. | 1. The product list will be displayed corresponding to the page number. | Login with manager account or eatery owner and on the product page. | Passed | 2024-03-18 | LongCH | Passed | 2024-03-23 | LongCH | 2024-03-27 | Passed | LongCH
Product_3 | Test view list products with paging. | 1.Click "1","2",.. button. | 1. The product list will be displayed corresponding to the page number. | Login with manager account or eatery owner and on the product page. | Failed | 2024-03-18 | LongCH | Failed | 2024-03-23 | LongCH | 2024-03-27 | Passed | LongCH
Product_4 | Test search list product. | 1.Enter the keyword to search. | 1. Display product list by keyword. | Login with manager account or eatery owner and on the product page. | Failed | 2024-03-18 | LongCH | Failed | 2024-03-23 | LongCH | 2024-03-27 | Passed | LongCH

## Create Product
Feature | Create Product
Test requirement | Create product
Number of TCs | 10
Testing Round | Passed | Failed | Pending | N/A
Round 1 | 10 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Create Product
Product_5 | Test UI create product. | 1. Click on "Thêm mới" button on screen. | 1. Create product pop-up is displayed with fields "Danh mục", "Tên sản phẩm", "Giá", "Trạng thái", "Ảnh" and button "Tải Ảnh Lên","Đóng","Lưu". | Login with manager account or eatery owner , go to the product page. | Failed | 2024-03-18 | LongCH | Failed | 2024-03-23 | LongCH | Passed | 2024-03-27 | LongCH
Product_6 | Test create product successfully | 1. Enter input: - Danh mục : Món ăn phụ - Tên sản phẩm : Nước ngọt - Giá : 20000 - Trạng thái : Đang kinh doanh - Ảnh : Pizza.png 2. Click "Lưu" | 1. Pop-up is "Thêm mới thành công". 2. The product is added to the product list. | Login with manager account or eatery owner, go to the product page and enter pop-up "Thêm mới". | Passed | 2024-03-18 | LongCH | Passed | 2024-03-23 | LongCH | Passed | 2024-03-27 | LongCH
Product_7 | Test create product with do not select "Trạng thái" | 1. Enter input: - Danh mục : Món ăn phụ - Tên sản phẩm : Nước ngọt - Giá : 20000 - Trạng thái : - Ảnh : Pizza.png 2. Click "Lưu" | 1. Pop-up is "Thêm mới thành công" and the product is added to the product list with "Trạng thái" : Ngừng kinh doanh. | Login with manager account or eatery owner, go to the product page and enter pop-up "Thêm mới". | Failed | 2024-03-18 | LongCH | Failed | 2024-03-23 | LongCH | Passed | 2024-03-27 | LongCH
Product_8 | Test create product with Danh mục , Tên sản phẩm, Trạng thái,Giá ,Ảnh empty | 1. Enter input: - Danh mục : - Tên sản phẩm : - Giá : - Trạng thái : - Ảnh : 2. Click "Lưu" | 1. Fields "Danh mục", "Tên sản phẩm", "Giá", "Ảnh" will appear with red ticks and the mock-up "Thêm mới" is still display. | Login with manager account or eatery owner, go to the product page and enter pop-up "Thêm mới". | Failed | 2024-03-18 | LongCH | Passed | 2024-03-23 | LongCH | Passed | 2024-03-27 | LongCH
Product_9 | Test create product with do not select "Danh mục" | 1.Enter input: - Danh mục : - Tên sản phẩm : Hamburger - Giá : 35000 - Trạng thái : Đang kinh doanh - Ảnh : hamburger.jpg 2. Click "Lưu" | 1. Fields "Danh mục" will appear with red ticks and the mock-up "Thêm mới" is still display. | Login with manager account or eatery owner, go to the product page and enter pop-up "Thêm mới". | Passed | 2024-03-18 | LongCH | Passed | 2024-03-23 | LongCH | Passed | 2024-03-27 | LongCH
Product_10 | Test create product with "Tên sản phẩm" : empty | 1. Enter input: -Danh mục:"Món ăn phụ" - Tên sản phẩm : - Giá : 25000 -Trạng thái : Đang kinh doanh - Ảnh : image.jpg 2. Click "Lưu" | 1. Fields "Tên sản phẩm" will appear with red ticks and the mock-up "Thêm mới" is still display. | Login with manager account or eatery owner, go to the product page and enter pop-up "Thêm mới". | Passed | 2024-03-18 | LongCH | Passed | 2024-03-23 | LongCH | Passed | 2024-03-27 | LongCH
Product_11 | Test create product with "Giá" : empty | 1. Enter input: -Danh mục:"Món ăn phụ" - Tên sản phẩm : "Cơm tấm" - Giá : -Trạng thái : Đang kinh doanh - Ảnh : image.jpg 2.Click "Lưu" | 1. Fields "Giá" will appear with red ticks and the mock-up "Thêm mới" is still display. | Login with manager account or eatery owner, go to the product page and enter pop-up "Thêm mới". | Failed | 2024-03-18 | LongCH | Passed | 2024-03-23 | LongCH | Passed | 2024-03-27 | LongCH
Product_12 | Test create product with "Ảnh" : empty | 1. Enter input: - Danh mục:"Món ăn phụ" - Tên sản phẩm : "Cơm tấm" - Giá : 25000 - Trạng thái : Đang kinh doanh - Ảnh : 2. Click "Lưu" | 1. Fields "Ảnh" will appear with red ticks and the mock-up "Thêm mới" is still display. | Login with manager account or eatery owner, go to the product page and enter pop-up "Thêm mới". | Failed | 2024-03-18 | LongCH | Failed | 2024-03-23 | LongCH | Passed | 2024-03-27 | LongCH
Product_13 | Test create product with function "Tải Ảnh Lên" | 1. Enter input: - Danh mục:"Món ăn phụ" - Tên sản phẩm : "Cơm tấm" - Giá : 27000 - Trạng thái : Đang kinh doanh - Ảnh : Click "Tải Ảnh Lên" , add image 2. Click "Lưu" | 1. Pop-up "Thêm mới thành công" is display and the product is added to the product list. | Login with manager account or eatery owner, go to the product page and enter pop-up "Thêm mới". | Failed | 2024-03-18 | LongCH | Failed | 2024-03-23 | LongCH | Passed | 2024-03-27 | LongCH
Product_14 | Test create product with "Giá" is not number | 1. Enter input: - Danh mục:"Món ăn phụ" - Tên sản phẩm : "Cơm tấm" - Giá : "ABCC" - Trạng thái : Đang kinh doanh - Ảnh : image.jpg 2. Click "Lưu" | 1. Pop-up "Thêm mới thất bại" is display and redirect to "Thêm mới" screen. | Login with manager account or eatery owner, go to the product page and enter pop-up "Thêm mới". | Failed | 2024-03-18 | LongCH | Failed | 2024-03-23 | LongCH | Passed | 2024-03-27 | LongCH

## Update Product
Feature | Update Product
Test requirement | Update product
Number of TCs | 9
Testing Round | Passed | Failed | Pending | N/A
Round 1 | 9 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Update Product
Product_15 | Test UI update product. | 1. Click icon update of product in each line of product. | 1. Update product pop-up is displayed with fields "Danh mục" , "Tên sản phẩm", "Giá", "Trạng thái", "Ảnh" with data, button "Đóng" , "Lưu". | Login with manager account or eatery owner , go to the product page. | Failed | 2024-03-18 | LongCH | Failed | 2024-03-23 | LongCH | Passed | 2024-03-27 | LongCH
Product_16 | Test update product with change "Danh mục". | 1. Change "Danh mục" of this product. 2. Click "Lưu". | 1. Pop-up "Cập nhập thành công" is display. 2. Redirect to list product screen. 3. "Danh mục" of this product change. | Login with manager account or eatery owner, go to the product page and choose product to update. | Passed | 2024-03-18 | LongCH | Passed | 2024-03-23 | LongCH | Passed | 2024-03-27 | LongCH
Product_17 | Test update product with change "Tên sản phẩm" | 1. Change "Tên sản phẩm" of this product. 2. Click "Lưu". | 1. Pop-up "Cập nhập thành công" is display. 2. Redirect to list product screen. 3. "Tên sản phẩm" of this product change. | Login with manager account or eatery owner, go to the product page and choose product to update. | Failed | 2024-03-18 | LongCH | Failed | 2024-03-23 | LongCH | Passed | 2024-03-27 | LongCH
Product_18 | Test update product with change "Giá" is number | 1. Change "Giá" of this product. 2. Click "Lưu". | 1. Pop-up "Cập nhập thành công" is display. 2. Redirect to list product screen. 3. "Giá" of this product change. | Login with manager account or eatery owner, go to the product page and choose product to update. | Passed | 2024-03-18 | LongCH | Passed | 2024-03-23 | LongCH | Passed | 2024-03-27 | LongCH
Product_19 | Test update product with change "Giá" is not number | 1. Change "Giá" of this product is "ABCCC". 2. Click "Lưu". | 1. Pop-up "Lỗi. Xin vui lòng thử lại" is display. 2. Redirect to "Chỉnh sửa" screen. | Login with manager account or eatery owner, go to the product page and choose product to update. | Failed | 2024-03-18 | LongCH | Passed | 2024-03-23 | LongCH | Passed | 2024-03-27 | LongCH
Product_20 | Test update product with change "Trạng thái" | 1. Change "Trạng thái" of this product. 2. Click "Lưu". | 1. Pop-up "Cập nhập thành công" is display. 2. Redirect to list product screen. 3. "Trạng thái" of this product change. | Login with manager account or eatery owner, go to the product page and choose product to update. | Passed | 2024-03-18 | LongCH | Passed | 2024-03-23 | LongCH | Passed | 2024-03-27 | LongCH
Product_21 | Test update product with change "Ảnh" | 1. Change "Ảnh" of this product. 2. Click "Lưu" | 1. Pop-up "Cập nhập thành công" is display. 2. Redirect to list product screen. 3. "Ảnh" of this product change. | Login with manager account or eatery owner, go to the product page and choose product to update. | Failed | 2024-03-18 | LongCH | Passed | 2024-03-23 | LongCH | Passed | 2024-03-27 | LongCH
Product_22 | Test update product with change "Ảnh" when click button "Tải Ảnh Lên" | 1. Choose "Ảnh" from device and click "Open". 2. Click "Lưu". | 1. Pop-up "Cập nhập thành công" is display. 2. Redirect to list product screen. 3. "Ảnh" of this product change. | Login with manager account or eatery owner, go to the product page and choose product to update, click button "Tải ảnh lên". | Failed | 2024-03-18 | LongCH | Failed | 2024-03-23 | LongCH | Passed | 2024-03-27 | LongCH
Product_23 | Test update product with change all "Danh mục", "Giá", "Trạng thái", "Tên sản phẩm", "Ảnh" | 1. Change all product data fields. | 1. Pop-up "Cập nhập thành công" is display. 2. Redirect to list product screen. 3. "Danh mục", "Giá", "Trạng thái", "Tên sản phẩm", "Ảnh" of this product change. | Login with manager account or eatery owner, go to the product page and choose product to update. | Failed | 2024-03-18 | LongCH | Failed | 2024-03-23 | LongCH | Passed | 2024-03-27 | LongCH

## View Detail Product
Feature | View Detail Product
Test requirement | View Detail Product
Number of TCs | 1
Testing Round | Passed | Failed | Pending | N/A
Round 1 | 1 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
View Detail Product
Product_24 | Test view detail product | 1.Click on icon detail. | 1. View detail product pop-up is displayed with fields "Tên sản phẩm" , "Giá" , "Danh mục" with data. | Login with manager account , go to the product page ,choose product. | Failed | 2024-03-19 | LongCH | Passed | 2024-03-23 | LongCH | Passed | 2024-03-27 | LongCH

## View List Category
Feature | View List Category
Test requirement | View List Category
Number of TCs | 4
Testing Round | Passed | Failed | Pending | N/A
Round 1 | 4 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
View List Product
Category_1 | Test view list category. | 1. Click on "Danh mục" button on left-corner menu. | 1. Category list screen is displayed with fields "Số thứ tự", "Tên danh mục" , "Trạng thái" , "Quản lý". | Login with manager account. | Passed | 2024-03-19 | LongCH | Passed | 2024-03-24 | LongCH | Passed | 2024-03-28 | LongCH
Category_2 | Test view list categorys with paging. | 1.Click "<<" ">>" button. | 1. The category list will be displayed corresponding to the page number. | Login with manager account and on the category page. | Failed | 2024-03-19 | LongCH | Failed | 2024-03-24 | LongCH | Passed | 2024-03-28 | LongCH
Category_3 | Test view list categorys with paging. | 1.Click "1","2",.. button. | 1. The category list will be displayed corresponding to the page number. | Login with manager account and on the category page. | Failed | 2024-03-19 | LongCH | Passed | 2024-03-24 | LongCH | Passed | 2024-03-28 | LongCH
Category_4 | Test search list category. | 1.Enter the keyword to search. | 1. Display category list by keyword. | Login with manager account and on the category page. | Passed | 2024-03-19 | LongCH | Passed | 2024-03-24 | LongCH | Passed | 2024-03-28 | LongCH

## Create Category
Feature | Create Category
Test requirement | Create Category
Number of TCs | 4
Testing Round | Passed | Failed | Pending | N/A
Round 1 | 4 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Create Category
Category_5 | Test UI create category. | 1. Click on "Thêm mới" button. | 1. Create category pop-up is displayed with fields "Danh mục" , "Trạng thái" and button "Đóng","Lưu". | Login with manager account , go to the category page. | Failed | 2024-03-19 | LongCH | Passed | 2024-03-24 | LongCH | Passed | 2024-03-28 | LongCH
Category_6 | Test create category successfully. | 1. Enter input: - Danh mục : Món ngọt - Trạng thái : Đang kinh doanh. 2. Click "Lưu". | 1. Pop-up is "Thành công". 2. The category is added to the category list. | Login with manager account and go to the category page and enter pop-up "Thêm mới". | Failed | 2024-03-19 | LongCH | Passed | 2024-03-24 | LongCH | Passed | 2024-03-28 | LongCH
Category_7 | Test create category with no select "Trạng thái". | 1. Enter input: - Danh mục : Món mặn. - Trạng thái : 2. Click "Lưu". | 1. Fields "Trạng thái" will appear with red ticks and the mock-up "Thêm mới" is still display. | Login with manager account and go to the category page and enter pop-up "Thêm mới". | Passed | 2024-03-19 | LongCH | Passed | 2024-03-24 | LongCH | Passed | 2024-03-28 | LongCH
Category_8 | Test create category with "Danh mục" is empty. | 1. Enter input: - Danh mục : - Trạng thái : Đang kinh doanh. 2. Click "Lưu". | 1. Fields "Danh mục" will appear with red ticks. 2. The mock-up "Thêm mới" is still display. | Login with manager account and go to the category page and enter pop-up "Thêm mới". | Failed | 2024-03-19 | LongCH | Failed | 2024-03-24 | LongCH | Passed | 2024-03-28 | LongCH

## Update Category
Feature | Update Category
Test requirement | Update Category
Number of TCs | 4
Testing Round | Passed | Failed | Pending | N/A
Round 1 | 4 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Update Category
Category_9 | Test UI update category. | 1. Click icon update in each line of category. | 1. Update category pop-up is displayed with fields "Danh mục" , "Trạng thái" with data, button "Đóng" , "Lưu". | Login with manager account and go to category page. | Failed | 2024-03-19 | LongCH | Failed | 2024-03-24 | LongCH | Passed | 2024-03-28 | LongCH
Category_10 | Test update category with change "Danh mục". | 1. Change "Danh mục" of this category. 2. Click "Lưu". | 1. Pop-up "Cập nhập thành công" is display. 2. Redirect to list category screen. 3. "Danh mục" of this category change. | Login with manager account and go to category page and choose category to update. | Passed | 2024-03-19 | LongCH | Passed | 2024-03-24 | LongCH | Passed | 2024-03-28 | LongCH
Category_11 | Test update category with change "Trạng thái" | 1. Change "Trạng thái" of this category. 4. Click "Lưu". | 1. Pop-up "Cập nhập thành công" is display. 2. Redirect to list category screen. 3. "Trạng thái" of this category change. | Login with manager account and go to category page and choose category to update. | Failed | 2024-03-19 | LongCH | Passed | 2024-03-24 | LongCH | Passed | 2024-03-28 | LongCH
Category_12 | Test update category with change "Danh mục", "Trạng thái" | 1. Change "Danh mục" and "Trạng thái" of this category. 2. Click "Lưu". | 1. Pop-up "Cập nhập thành công" is display. 2. Redirect to list category screen. 3. "Danh mục" , "Trạng thái" of this category change. | Login with manager account and go to category page and choose category to update. | Passed | 2024-03-19 | LongCH | Passed | 2024-03-24 | LongCH | Passed | 2024-03-28 | LongCH

## View Detail Category
Feature | View Detail Category
Test requirement | View Detail Category
Number of TCs | 1
Testing Round | Passed | Failed | Pending | N/A
Round 1 | 1 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
View Detail Category
Category_13 | Test view detail category | 1.Click on icon detail of this category. | 1. View detail category pop-up is displayed with fields "Danh mục", "Trạng thái" with data. | Login with manager account , go to the category page ,choose category. | Passed | 2024-03-19 | LongCH | Passed | 2024-03-24 | LongCH | Passed | 2024-03-28 | LongCH

## View List User
Feature | View List User
Test requirement | View List User
Number of TCs | 4
Testing Round | Passed | Failed | Pending | N/A
Round 1 | 4 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
View List User
User_1 | Test view list user. | 1. Click on "Nhân Viên" button on left-corner in menu. | User list for manager screen is displayed. | Login in system. | Passed | 2024-03-20 | LongCH | Passed | 2024-03-24 | LongCH | Passed | 2024-03-28 | LongCH
User_2 | Test view list user with paging. | 1. Click "<<" ">>" button. | 1. The user list will be displayed corresponding to the page number. | Login in system, go to user page. | Failed | 2024-03-20 | LongCH | Passed | 2024-03-24 | LongCH | Passed | 2024-03-28 | LongCH
User_3 | Test view list user with paging. | 1. Click "1","2",.. button. | 1. The user list will be displayed corresponding to the page number. | Login in system, go to user page. | Failed | 2024-03-20 | LongCH | Passed | 2024-03-24 | LongCH | Passed | 2024-03-28 | LongCH
User_4 | Test search list user | 1. Enter the keyword to search. | 1. Display user list by keyword. | Login in system, go to user page. | Failed | 2024-03-20 | LongCH | Failed | 2024-03-24 | LongCH | Passed | 2024-03-28 | LongCH

## Create User
Feature | Create User
Test requirement | Create User
Number of TCs | 10
Testing Round | Passed | Failed | Pending | N/A
Round 1 | 10 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
User_5 | Test UI create user. | 1. Click on "Thêm mới" button. | 1. The create pop-up will display with: + Họ tên. + Tài khoản. + Số điện thoại. + Email. + Phân quyền. | Login in system , go to page user. | Failed | 2024-03-20 | LongCH | Failed | 2024-03-24 | LongCH | Passed | 2024-03-28 | LongCH
User_6 | Test create user successfully. | 1. Enter input: - Họ tên : nguyễn khánh - Tài khoản : khanh_2345 - Số điện thoại : 0978124523 - Email : khanh_3456@gmail.com - Phân quyền : Admin. 2. Click "Lưu". | 1. Pop-up is "Thành công" and the user is added to the user list. | Login in system , go to page user and enter pop-up "Thêm mới". | Failed | 2024-03-20 | LongCH | Passed | 2024-03-24 | LongCH | Passed | 2024-03-28 | LongCH
User_7 | Test create user with blank "Họ tên" | 1. Enter input: - Họ tên : - Tài khoản : huy_234598 - Số điện thoại : 0978147624 - Email : huy_343456@gmail.com - Phân quyền : Admin. 2. Click "Lưu". | 1. Fields "Họ tên" will appear with red ticks and the mock-up "Thêm mới" is still display. | Login in system , go to page user and enter pop-up "Thêm mới". | Failed | 2024-03-20 | LongCH | Failed | 2024-03-24 | LongCH | Passed | 2024-03-28 | LongCH
User_8 | Test create user with "Họ tên" have one character | 1. Enter input: - Họ tên : h - Tài khoản : huy_234598 - Số điện thoại : 0978147624 - Email : huy_343456@gmail.com - Phân quyền : Admin. 2. Click "Lưu". | 1. Fields "Họ tên" will appear with red ticks and the mock-up "Thêm mới" is still display. | Login in system , go to page user and enter pop-up "Thêm mới". | Passed | 2024-03-20 | LongCH | Passed | 2024-03-24 | LongCH | Passed | 2024-03-28 | LongCH
User_9 | Test create user with blank "Tài khoản" | 1. Enter input: - Họ tên : cao ha - Tài khoản : - Số điện thoại : 0978123435 - Email : hacao_234@gmail.com - Phân quyền : Chef. 2. Click "Lưu". | 1. Fields "Tài khoản" will appear with red ticks and the mock-up "Thêm mới" is still display. | Login in system , go to page user and enter pop-up "Thêm mới". | Passed | 2024-03-20 | LongCH | Passed | 2024-03-24 | LongCH | Passed | 2024-03-28 | LongCH
User_10 | Test create user with blank "Số điện thoại" | 1. Enter input: - Họ tên : cao ha - Tài khoản : hacao_456 - Số điện thoại : - Email : hacao_234@gmail.com - Phân quyền : Chef. 2. Click "Lưu". | 1. Fields "Số điện thoại" will appear with red ticks and the mock-up "Thêm mới" is still display. | Login in system , go to page user and enter pop-up "Thêm mới". | Failed | 2024-03-20 | LongCH | Failed | 2024-03-24 | LongCH | Passed | 2024-03-28 | LongCH
User_11 | Test create user with "Số điện thoại" is not number. | 1. Enter input: - Họ tên : nguyen huy - Tài khoản : huynguyen_789 - Số điện thoại : ABCCC - Email : huynguyen_789@gmail.com - Phân quyền : Waiter. 2. Click "Lưu". | 1. Fields "Số điện thoại" will appear with red ticks and the mock-up "Thêm mới" is still display. | Login in system , go to page user and enter pop-up "Thêm mới". | Failed | 2024-03-20 | LongCH | Passed | 2024-03-24 | LongCH | Passed | 2024-03-28 | LongCH
User_12 | Test create user with "Số điện thoại" is number and not have 10 digits. | 1. Enter input: - Họ tên : nguyen huy - Tài khoản : huynguyen_789 - Số điện thoại : 09345687245 - Email : huynguyen_789@gmail.com - Phân quyền : Waiter. 2. Click "Lưu". | 1. Fields "Số điện thoại" will appear with red ticks and the mock-up "Thêm mới" is still display. | Login in system , go to page user and enter pop-up "Thêm mới". | Failed | 2024-03-20 | LongCH | Passed | 2024-03-24 | LongCH | Passed | 2024-03-28 | LongCH
User_13 | Test create user with blank "Email". | 1. Enter input: - Họ tên : nguyen huy - Tài khoản : huynguyen_789 - Số điện thoại : 09345687245 - Email : - Phân quyền : Waiter. 2. Click "Lưu". | 1. Fields "Email" will appear with red ticks and the mock-up "Thêm mới" is still display. | Login in system , go to page user and enter pop-up "Thêm mới". | Passed | 2024-03-20 | LongCH | Passed | 2024-03-24 | LongCH | Passed | 2024-03-28 | LongCH
User_14 | Test create user with not select "Phân quyền". | 1. Enter input: - Họ tên : nguyen huy - Tài khoản : huynguyen_789 - Số điện thoại : 09345687245 - Email : huynv@gmail.com - Phân quyền : 2. Click "Lưu". | 1. Fields "Phân quyền" will appear with red ticks and the mock-up "Thêm mới" is still display. | Login in system , go to page user and enter pop-up "Thêm mới". | Passed | 2024-03-20 | LongCH | Passed | 2024-03-24 | LongCH | Passed | 2024-03-28 | LongCH

## Update User
Feature | Update User
Test requirement | Update User
Number of TCs | 9
Testing Round | Passed | Failed | Pending | N/A
Round 1 | 9 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
User_15 | Test UI update category. | 1. Click icon update of in each line of user. | 1. The edit user dialog will display with information of current user: "Họ tên", "Tài khoản", "Số điện thoại", "Email", "Phân quyền" with data and button "Đóng" ,"Lưu" | Login in system, go to user page and choose user. | Failed | 2024-03-20 | LongCH | Failed | 2024-03-25 | LongCH | Passed | 2024-03-29 | LongCH
User_16 | Test update user with change "Họ tên" | 1. Change "Họ tên" of this user. 2. Click "Lưu". | 1. Pop-up "Sửa thành công" is display. 2. Redirect to list user screen. 3. "Họ tên" of this product change. | Login in system, go to user page and choose user to update. | Passed | 2024-03-20 | LongCH | Passed | 2024-03-25 | LongCH | Passed | 2024-03-29 | LongCH
User_17 | Test update user with "Họ tên" blank | 1. Do not enter data for "Họ tên" fields. 2. Click "Lưu". | 1. Fields "Họ tên" will appear with red ticks. 2. The mock-up "Chỉnh sửa" is still display. | Login in system, go to user page and choose user to update. | Failed | 2024-03-20 | LongCH | Passed | 2024-03-25 | LongCH | Passed | 2024-03-29 | LongCH
User_18 | Test update user with change "Tài khoản" | 1. Change "Tài khoản" of this user. 2. Click "Lưu". | 1. Pop-up "Sửa thành công" is display. 2. Redirect to list user screen. 3. "Tài khoản" of this product change. | Login in system, go to user page and choose user to update. | Failed | 2024-03-20 | LongCH | Failed | 2024-03-25 | LongCH | Passed | 2024-03-29 | LongCH
User_19 | Test update user with "Tài khoản" is blank | 1. Do not enter data for "Tài khoản" fields. 2. Click "Lưu". | 1. Fields "Tài khoản" will appear with red ticks. 2. The mock-up "Chỉnh sửa" is still display. | Login in system, go to user page and choose user to update. | Passed | 2024-03-20 | LongCH | Passed | 2024-03-25 | LongCH | Passed | 2024-03-29 | LongCH
User_20 | Test update user with "Số điện thoại" blank | 1. Do not enter data for "Số điện thoại" fields. 2. Click "Lưu". | 1. Fields "Tài khoản" will appear with red ticks. 2. The mock-up "Chỉnh sửa" is still display. | Login in system, go to user page and choose user to update. | Failed | 2024-03-20 | LongCH | Passed | 2024-03-25 | LongCH | Passed | 2024-03-29 | LongCH
User_21 | Test update user with change "Số điện thoại" have 10 digits | 1. Change "Số điện thoại" have 10 digits. 4. Click "Lưu". | 1. Pop-up "Thành công" is display. 2. Redirect to list user screen. 3. "Số điện thoại" of this product change. | Login in system, go to user page and choose user to update. | Failed | 2024-03-20 | LongCH | Passed | 2024-03-25 | LongCH | Passed | 2024-03-29 | LongCH
User_22 | Test update user with change "Số điện thoại" not have 10 digits | 1. Change "Số điện thoại" with have 11 digits 2. Click "Lưu". | 1. Fields "Số điện thoại" will appear with red ticks. 2. The mock-up "Chỉnh sửa" is still display. | Login in system, go to user page and choose user to update. | Passed | 2024-03-20 | LongCH | Passed | 2024-03-25 | LongCH | Passed | 2024-03-29 | LongCH
User_23 | Test update user with "Số điện thoại" have letters | 1. Change "Số điện thoại" with have letters. 2. Click "Lưu". | 1. Fields "Số điện thoại" will appear with red ticks. 2. The mock-up "Chỉnh sửa" is still display. | Login in system, go to user page and choose user to update. | Failed | 2024-03-20 | LongCH | Failed | 2024-03-25 | LongCH | Passed | 2024-03-29 | LongCH

## View Detail User
Feature | View Detail User
Test requirement | View Detail User
Number of TCs | 1
Testing Round | Passed | Failed | Pending | N/A
Round 1 | 1 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
User_16 | Test view detail user | 1.Click on icon detail. | 1. View detail user pop-up is displayed with fields "Họ tên", "Email", "Số điện thoại", "Tài khoản","Phân quyền" with data. | Login in system, go to user page and choose user. | Failed | 2024-03-20 | LongCH | Passed | 2024-03-25 | LongCH | Passed | 2024-03-29 | LongCH

## View List Table
Feature | View List Table
Test requirement | View List Table
Number of TCs | 3
Testing Round | Passed | Failed | Pending | N/A
Round 1 | 3 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Table_1 | Test view list tables. | 1. Click on "Quản lý bàn" button on left-corner menu. | 1. Table list for manager screen is displayed with "Số thứ tự", "Tên bàn","Vị trí","Trạng thái", "Quản lý" fields. | Login with manager account. | Passed | 2024-03-20 | LongCH | Passed | 2024-03-25 | LongCH | Passed | 2024-03-29 | LongCH
Table_2 | Test view list tables with paging. | 1.Click "<<" ">>" button. | 1. The table list will be displayed corresponding to the page number. | Login with manager account and go to table page. | Failed | 2024-03-20 | LongCH | Failed | 2024-03-25 | LongCH | Passed | 2024-03-29 | LongCH
Table_3 | Test view list tables with paging. | 1.Click "1","2",.. button. | 1. The table list will be displayed corresponding to the page number. | Login with manager account and go to table page. | Failed | 2024-03-20 | LongCH | Failed | 2024-03-25 | LongCH | Passed | 2024-03-29 | LongCH

## Create Table
Feature | Create Table
Test requirement | Create Table
Number of TCs | 4
Testing Round | Passed | Failed | Pending | N/A
Round 1 | 4 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Table_4 | Test UI create table. | 1. Click "Thêm mới" button. | 1. The create pop-up will display with "Tên bàn", "Vị trí", "Trạng thái" and "Lưu", "Đóng" button. | Login with manager account, go to table page. | Failed | 2024-03-20 | LongCH | Failed | 2024-03-25 | LongCH | Passed | 2024-03-29 | LongCH
Table_5 | Test create table successfully | 1. Enter input: - Tên bàn : Bàn 11 - Vị trí : Tầng 2 - Trạng thái : Trống 2. Click "Lưu" | 1. Pop-up is "Thêm mới thành công". 2. The table is added to the table list. | Login with manager account, go to table page, enter pop-up "Thêm mới" | Failed | 2024-03-20 | LongCH | Failed | 2024-03-25 | LongCH | Passed | 2024-03-29 | LongCH
Table_6 | Test create table with blank "Tên bàn". | 1. Do not enter "Tên bàn". 2. Click "Lưu". | 1. Fields "Tên bàn" will appear with red ticks and the mock-up "Thêm mới" is still display. | Login with manager account, go to table page, enter pop-up "Thêm mới" | Passed | 2024-03-20 | LongCH | Passed | 2024-03-25 | LongCH | Passed | 2024-03-29 | LongCH
Table_7 | Test create table with no select "Vị trí". | 1. Do not select "Vị trí" of table. 2. Click "Lưu". | 1. Fields "Vị trí" will appear with red ticks and the mock-up "Thêm mới" is still display. | Login with manager account, go to table page, enter pop-up "Thêm mới" | Failed | 2024-03-20 | LongCH | Failed | 2024-03-25 | LongCH | Passed | 2024-03-29 | LongCH

## Update Table
Feature | Update Table
Test requirement | Update Table
Number of TCs | 4
Testing Round | Passed | Failed | Pending | N/A
Round 1 | 4 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Table_8 | Test UI update table. | 1. Click icon update of table in each line. | 1. The update table pop-up will display "Tên bàn" , "Vị trí" , "Trạng thái" and "Đóng" , "Lưu" button with data. | Login with manager account, go to table page, choose table to update. | Failed | 2024-03-21 | LongCH | Failed | 2024-03-25 | LongCH | Passed | 2024-03-29 | LongCH
Table_9 | Test change name of table. | 1. Change name of this table. 2. Click "Lưu". | 1. Pop-up "Sửa thành công" is display and name of this table will change. | Login with manager account, go to table page, choose table to update. | Failed | 2024-03-21 | LongCH | Failed | 2024-03-25 | LongCH | Passed | 2024-03-29 | LongCH
Table_10 | Test change "Vị trí" of table. | 1. Change "Vị trí" of this table. 2. Click "Lưu". | 1. Pop-up "Sửa thành công" is display and name of this table will change. | Login with manager account, go to table page, choose table to update. | Passed | 2024-03-21 | LongCH | Passed | 2024-03-25 | LongCH | Passed | 2024-03-29 | LongCH
Table_11 | Test update name category is blank. | 1. Name of this table is blank. 2. Click "Lưu". | 1. Notification of red ticks and "Thêm mới" pop-up is still display. | Login with manager account, go to table page, choose table to update. | Passed | 2024-03-21 | LongCH | Passed | 2024-03-25 | LongCH | Passed | 2024-03-29 | LongCH

## View Menu
Feature | View Menu
Test requirement | View Menu
Number of TCs | 6
Testing Round | Passed | Failed | Pending | N/A
Round 1 | 6 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
View Menu
Menu_1 | Test view menu. | 1. Click on table. | 1. All products is displayed. | 1.Login with waiter account and enter "Bàn" page or login with customer and enter "Thực đơn". | Failed | 2024-03-21 | LongCH | Failed | 2024-03-25 | LongCH | Passed | 2024-03-29 | LongCH
Menu_2 | Test view menu with filter by category "Món chính". | 1. Click on "Thực đơn" button in waiter or click button "☰" in customer. 2. Select category "Món chính". | 1. All products filter by category "Món chính" will be displayed. | 1. Login with waiter account ,enter "Bàn" page and choose table or login with customer. | Failed | 2024-03-21 | LongCH | Failed | 2024-03-25 | LongCH | Passed | 2024-03-29 | LongCH
Menu_3 | Test view menu with filter by category "Món tráng miệng". | 1. Click on "Thực đơn" button in waiter or click button "☰" in customer. 2. Select category "Món tráng miệng". | 1. All products filter by category "Món tráng miệng" will be displayed. | Login with waiter account ,enter "Bàn" page and choose table or login with customer. | Failed | 2024-03-21 | LongCH | Failed | 2024-03-25 | LongCH | Passed | 2024-03-29 | LongCH
Menu_4 | Test view menu with filter by category "Nước giải khát". | 1. Click on "Thực đơn" button in waiter or click button "☰" in customer. 2. Select category "Nước giải khát". | 1. All products filter by category "Nước giải khát" will be displayed. | Login with waiter account ,enter "Bàn" page and choose table or login with customer. | Failed | 2024-03-21 | LongCH | Failed | 2024-03-25 | LongCH | Passed | 2024-03-29 | LongCH
Menu_5 | Test view menu with filter by category "Bia & Rượu" | 1. Click on "Thực đơn" button in waiter or click button "☰" in customer. 2. Select category "Bia & Rượu". | 1. All products filter by category "Bia & Rượu" will be displayed. | Login with waiter account ,enter "Bàn" page and choose table or login with customer. | Passed | 2024-03-21 | LongCH | Passed | 2024-03-25 | LongCH | Passed | 2024-03-29 | LongCH
Menu_6 | Test view menu with search by name. | 1. Enter the keyword to search. | 1. All products search by name will display. | Login with waiter account ,enter "Bàn" page and choose table or login with customer. | Failed | 2024-03-21 | LongCH | Failed | 2024-03-25 | LongCH | Passed | 2024-03-29 | LongCH

## View Cart
Feature | View Cart
Test requirement | View Cart
Number of TCs | 6
Testing Round | Passed | Failed | Pending | N/A
Round 1 | 6 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Function View Product In Cart
Cart_4 | Test view list product in cart. | 1. Click "Giỏ hàng" button. | 1. List product in cart will be displayed. | Login with waiter account , go to table page , choose table and order,click "Giỏ hàng" button. | Failed | 2024-03-21 | LongCH | Failed | 2024-03-26 | LongCH | Passed | 2024-03-30 | LongCH
Function Update Cart
Cart_5 | Test increase number of product in cart | 1. Click button "+" . | 1. Number of product is increases. | Login with waiter account , go to table page , choose table and order,click "Giỏ hàng" button. | Failed | 2024-03-21 | LongCH | Passed | 2024-03-26 | LongCH | Passed | 2024-03-30 | LongCH
Cart_6 | Test reduce number of product in cart. | 1. Click button "-" | 1. Number of product is reduce | Login with waiter account , go to table page , choose table and order,click "Giỏ hàng" button. | Failed | 2024-03-21 | LongCH | Passed | 2024-03-26 | LongCH | Passed | 2024-03-30 | LongCH
Cart_7 | Test delete product in cart | 1. Click icon delete in each line. | 1. This product will disappear. | Login with waiter account , go to table page , choose table and order,click "Giỏ hàng" button. | Passed | 2024-03-21 | LongCH | Passed | 2024-03-26 | LongCH | Passed | 2024-03-30 | LongCH
Cart_8 | Test click button "Thêm mới" in cart. | 1. Click button "Thêm mới" | 1. Navigate to the menu screen | Login with waiter account , go to table page , choose table and order,click "Giỏ hàng" button. | Failed | 2024-03-21 | LongCH | Failed | 2024-03-26 | LongCH | Passed | 2024-03-30 | LongCH
Cart_9 | Test click button "Tạo đơn" | 1. Click button "Tạo đơn". | 1. This order will be added to the order page. | Login with waiter account , go to table page , choose table and order,click "Giỏ hàng" button. | Failed | 2024-03-21 | LongCH | Passed | 2024-03-26 | LongCH | Passed | 2024-03-30 | LongCH

## Add To Cart
Feature | Add To Cart
Test requirement | Add To Cart
Number of TCs | 3
Testing Round | Passed | Failed | Pending | N/A
Round 1 | 3 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Cart_1 | Test add product to cart with number product > 0. | 1. Enter number of product is 3 | 1. Pop-up is "Thành công , đã thêm vào giỏ hàng". 2. The product is added to cart. | Login with waiter account or customer account, go to "Thực đơn" screen and choose product. | Passed | 2024-03-21 | LongCH | Passed | 2024-03-26 | LongCH | Passed | 2024-03-30 | LongCH
Cart_2 | Test add product to cart with number product <= 0 | 1. Click product and enter number of product is -2 | 1. Pop-up is "Thất bại , thêm vào giỏ hàng thất bại". | Login with waiter account or customer account, go to "Thực đơn" screen and choose product. | Passed | 2024-03-21 | LongCH | Passed | 2024-03-26 | LongCH | Passed | 2024-03-30 | LongCH
Cart_3 | Test add product to cart with number product is not number | 1. Enter number of product is "Abcd". | 1. "Abcd" will not be appear in textbox "Số lượng". | Login with waiter account or customer account, go to "Thực đơn" screen and choose product. | Passed | 2024-03-21 | LongCH | Passed | 2024-03-26 | LongCH | Passed | 2024-03-30 | LongCH

## View List Order Dish
Feature | View List Order Dish
Test requirement | View List Order Dish
Number of TCs | 5
Testing Round | Passed | Failed | Pending | N/A
Round 1 | 5 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Chef_1 | Test view list order dish | 1. Enter button "Theo món". | 1. Displays a list of dishes waiting to be processed with fields "Tên món", "Ghi chú", "Số lượng","Quản lý". | Login with chef account. | Failed | 2024-03-21 | LongCH | Failed | 2024-03-26 | LongCH | Passed | 2024-03-30 | LongCH
Chef_2 | Test transfer each dish awaiting processing to processing. | 1. Click button ">" in each line. | 1. That item will transfer the quantity of 1 item to the side that has been processed with fields "Tên món","Số lượng","Quản lý". | Login with chef account and click button "Theo món". | Failed | 2024-03-21 | LongCH | Failed | 2024-03-26 | LongCH | Passed | 2024-03-30 | LongCH
Chef_3 | Test convert all quantities of a product to processed. | 1. Click button ">>" in each line. | 1. The item will transfer all item quantities to the processed side with the fields "Item Name","Quantity","Management". | Login with chef account and click button "Theo món". | Passed | 2024-03-21 | LongCH | Passed | 2024-03-26 | LongCH | Passed | 2024-03-30 | LongCH
Chef_4 | Test transfer one product from finished screen to waiting for processing. | 1. Click button "<" in each line. | 1. That one product will return to the screen waiting for processing. | Login with chef account and click button "Theo món". | Passed | 2024-03-21 | LongCH | Passed | 2024-03-26 | LongCH | Passed | 2024-03-30 | LongCH
Chef_5 | Test move all products from the finished screen to the pending screen. | 1. Click button "<<" in each line. | 1. All product will return to the screen waiting for processing. | Login with chef account and click button "Theo món". | Failed | 2024-03-21 | LongCH | Pased | 2024-03-26 | LongCH | Passed | 2024-03-30 | LongCH

## View List Order
Feature | View List Order.
Test requirement | View List Order.
Number of TCs | 3
Testing Round | Passed | Failed | Pending | N/A
Round 1 | 3 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
VLO_1 | Test View List Order | 1. Click on "Giao dịch" button on left-corner in menu. | 1. Displays a list of dishes waiting to be processed with fields "Tên món", "Ghi chú", "Số lượng","Quản lý". | Login with account manager or eatery owner. | Passed | 2024-03-21 | LongCH | Passed | 2024-03-26 | LongCH | Passed | 2024-03-30 | LongCH
VLO_2 | Test view list order by paging. | 1. Click "<<" ">>" button. | 1. The order list will be displayed corresponding to the page number | Login with account manager or eatery owner. | Passed | 2024-03-21 | LongCH | Passed | 2024-03-26 | LongCH | Passed | 2024-03-30 | LongCH
VLO_3 | Test view list order by paging. | 1. Click "1" , "2" button. | 1. The order list will be displayed corresponding to the page number | Login with account manager or eatery owner. | Passed | 2024-03-21 | LongCH | Passed | 2024-03-26 | LongCH | Passed | 2024-03-30 | LongCH

## View Order Detail
Feature | View Order Detail.
Test requirement | View Order Detail.
Number of TCs | 1
Testing Round | Passed | Failed | Pending | N/A
Round 1 | 1 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
VOD_1 | Test View Order Detail | 1. Click on "Giao dịch" button on left-corner in menu. | 1. Displays a list of available dishes with the quantities in this order. | Login with account manager or eatery owner or cashier. | Passed | 2024-03-22 | LongCH | Passed | 2024-03-26 | LongCH | Passed | 2024-03-30 | LongCH

## View List Bill
Feature | View List Bill.
Test requirement | View List Bill.
Number of TCs | 3
Testing Round | Passed | Failed | Pending | N/A
Round 1 | 3 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
VLB_1 | Test View List Bill | 1. Click on "Thu ngân" button on left-corner in menu. | 1. Displays a list bill with fileds "Số thứ tự", "Tên khách", "Tổng món" , "Tổng tiền" , "Tên bàn" , "Quản lý". | Login with account cashier. | Passed | 2024-03-22 | LongCH | Passed | 2024-03-26 | LongCH | Passed | 2024-03-30 | LongCH
VLB_2 | Test view list bill with paging. | 1.Click "<<" ">>" button. | 1. The bill list will be displayed corresponding to the page number. | Login with account cashier. | Passed | 2024-03-22 | LongCH | Passed | 2024-03-26 | LongCH | Passed | 2024-03-30 | LongCH
VLB_3 | Test view list bill with paging. | 1.Click "1","2",.. button. | 1. The bill list will be displayed corresponding to the page number. | Login with account cashier. | Passed | 2024-03-22 | LongCH | Passed | 2024-03-26 | LongCH | Passed | 2024-03-30 | LongCH