## Cover
SYSTEM TEST REPORT DOCUMENT
Project Name | Eatery Management System |  |  | Creator | LongCH
Project Code | EMS |  |  | Issue Date | 2024-02-25
Document Code | Report5.3_System Test_v1.3 |  |  | Version | 1.3
Record of change
Effective Date | Version | Change Item | *A,D,M | Change description | Reference
2024-02-25 | 1.0 |  | A | Create System test file.
2024-04-01 | 1.1 |  | M | Update System test file.
2024-04-02 |  |  | M | Update System test file.
2024-04-03 |  |  | M | Update System test file.
2024-04-04 |  |  | M | Update System test file.
2024-04-05 | 1.2 |  | M | Update System test file.
2024-04-06 |  |  | M | Update System test file.
2024-04-07 |  |  | M | Update System test file.
2024-04-08 |  |  | M | Update System test file.
2024-04-09 | 1.3 |  | M | Update System test file.
2024-04-10 |  |  | M | Update System test file.
2024-04-11 |  |  | M | Update System test file.
2024-04-12 |  |  | M | Update System test file.

## Test Cases
TEST CASE LIST
Project Name |  | Eatery Management System
Project Code |  | EMS
Test Environment Setup Description |  | 1. Server 2. My SQL 3. Web Browser
No | Function Name | Sheet Name
1 | Login | Login
2 | Logout | Logout
3 | Manage Product | Manage Product
4 | Manage Category | Manage Category
5 | Manage User | Manager User
6 | Manage Table | Manage Table
7 | Manage Cart | Manage Cart
8 | Manage Order | Manager Order

## Test Statistics
TEST STATISTICS
Project Name | Eatery Management System |  | Creator |  | LongCH
Project Code | EMS |  | Reviewer/Approver |  | NAMLH
Document Code | Report5.3_System Test_v1.3 |  | Issue Date |  | 2024-02-25
Notes
No | Module code | Passed | Failed | Pending | N/A | Number of test cases
1 | Login | 6 | 0 | 0 | 0 | 6
2 | Logout | 3 | 0 | 0 | 0 | 3
3 | Manage Product | 12 | 0 | 0 | 0 | 12
4 | Manage Category | 9 | 0 | 0 | 0 | 9
5 | Manager User | 10 | 0 | 0 | 0 | 10
6 | Manage Table | 8 | 0 | 0 | 0 | 8
7 | Manage Cart | 7 | 0 | 0 | 0 | 7
8 | Manager Order | 2 | 0 | 0 | 0 | 2
| Sub total | 57 | 0 | 0 | 0 | 57
| Test coverage |  | 100 | %
| Test successful coverage |  | 100 | %

## Login
Workflow | Login
Test requirement | Login
Number of TCs | 6
Status | Passed | Failed | Pending | N/A
Total | 6 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Login
Login_1 | Test UI of login page. | 1. Navigate to Login screen. | 2. Login screen is display with "Tên đăng nhập", "Mật khẩu" and button "Đăng nhập". | Navigate to Login screen. | Passed | 2024-04-01 | LongCH | Passed | 2024-04-05 | LongCH | Passed | 2024-04-09 | LongCH
Login_2 | Test login successful with role waiter. | 1. Enter input: + Tên đăng nhập : waiter. + Mật khẩu : 123456aA. 2. Click button "Đăng nhập" | 3. Navigate to screen of role waiter. | Navigate to Login screen. | Failed | 2024-04-01 | LongCH | Failed | 2024-04-05 | LongCH | Passed | 2024-04-09 | LongCH
Login_3 | Test login successful with role manager. | 1. Enter input: + Tên đăng nhập : waiter. + Mật khẩu : 123456aA. 2. Click button "Đăng nhập" | 3. Navigate to screen of role manager. | Navigate to Login screen. | Passed | 2024-04-01 | LongCH | Passed | 2024-04-05 | LongCH | Passed | 2024-04-09 | LongCH
Login_4 | Test login with do not enter "Tên đăng nhập". | 1. Enter input: + Tên đăng nhập : + Mật khẩu : 123456aA. 2. Click button "Đăng nhập" | 3. The error message is display "Tên đăng nhập là bắt buộc" | Navigate to Login screen. | Failed | 2024-04-01 | LongCH | Failed | 2024-04-05 | LongCH | Passed | 2024-04-09 | LongCH
Login_5 | Test login with do not enter "Mật khẩu". | 1. Enter input: + Tên đăng nhập : admin + Mật khẩu : 2. Click button "Đăng nhập" | 3. The error message is display "Mật khẩu chưa được nhập" | Navigate to Login screen. | Passed | 2024-04-01 | LongCH | Passed | 2024-04-05 | LongCH | Passed | 2024-04-09 | LongCH
Login_6 | Test login with do not enter "Tên đăng nhập", "Mật khẩu". | 1. Enter input: + Tên đăng nhập : + Mật khẩu : 2. Click button "Đăng nhập" | 3. The error message is display "Tên đăng nhập là bắt buộc", "Mật khẩu chưa được nhập" . | Navigate to Login screen. | Failed | 2024-04-01 | LongCH | Failed | 2024-04-05 | LongCH | Passed | 2024-04-09 | LongCH

## Logout
Workflow | Logout
Test requirement | Logout
Number of TCs | 3
Status | Passed | Failed | Pending | N/A
Total | 3 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Login
Logout_1 | Test logout with role waiter. | 1. Click button "Logout". | 2. Return to the login screen | Login in system with role waiter. | Passed | 2024-04-01 | LongCH | Passed | 2024-04-05 | LongCH | Passed | 2024-04-09 | LongCH
Logout_2 | Test logout with role manager. | 1. Click button "Logout". | 2. Return to the login screen. | Login in system with role manager. | Passed | 2024-04-01 | LongCH | Passed | 2024-04-05 | LongCH | Passed | 2024-04-09 | LongCH
Logout_3 | Test logout with role owner eatery. | 1. Click button "Logout". | 2. Return to the login screen. | Login in system with role owner eatery. | Passed | 2024-04-01 | LongCH | Passed | 2024-04-05 | LongCH | Passed | 2024-04-09 | LongCH

## Manage Product
Workflow | Manage Product | [13 empty] | Passed
Test requirement | Manage Product | [13 empty] | Failed
Number of TCs | 12 | [13 empty] | Pending
Status | Passed | Failed | Pending | N/A | [10 empty] | N/A
Total | 12 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Manage Product
Manager_Product_1 | Test view list products. | 1. Click on "Sản phẩm" button on left-corner menu. | 1. Product list screen is displayed with fields "Số thứ tự", "Ảnh" , "Tên sản phẩm" , "Giá" , "Danh mục" , "Trạng thái" , "Quản lý". | Login with account manager or eatery owner role. | Passed | 2024-04-02 | LongCH | Passed | 2024-04-06 | LongCH | Passed | 2024-04-10 | LongCH
Manager_Product_2 | Test view UI of create products. | 1. Click on "Sản phẩm" button on left-corner menu. 3. Click button "Thêm mơi". | 2. Product list screen is displayed. 4. Create product pop-up is display with "Danh mục", "Tên sản phẩm", "Giá", "Trạng thái", "Ảnh" and button "Tải Ảnh Lên" , "Đóng" , "Lưu" | Login with account manager or eatery owner role. | Failed | 2024-04-02 | LongCH | Passed | 2024-04-06 | LongCH | Passed | 2024-04-10 | LongCH
Manager_Product_3 | Test create product successfully. | 1. Click on "Sản phẩm" button on left-corner menu. 3. Click button "Thêm mơi". 5. Enter input : - Danh mục : Món tráng miệng - Tến sản phẩm : Bánh gạo - Giá : 25000 - Trạng thái : Đanh kinh doanh. - Ảnh : image.jpg 6. Click button "Lưu". | 2. Product list screen is displayed. 4. Create product pop-up is display. 7. Pop-up "Thêm mới thành công" is display. | Login with account manager or eatery owner role. | Failed | 2024-04-02 | LongCH | Failed | 2024-04-06 | LongCH | Passed | 2024-04-10 | LongCH
Manager Product_4 | Test create product with do not select "Trạng thái". | 1. Click on "Sản phẩm" button on left-corner menu. 3. Click button "Thêm mơi". 5. Enter input : - Danh mục : Món ăn phụ - Tên sản phẩm : Nước ngọt - Giá : 30000 - Ảnh : Pizza.png 6. Click "Lưu". | 2. Product list screen is displayed. 4. Create product pop-up is display. 7. Pop-up "Thêm mới thành công" and the product is added to the product list with "Trạng thái" : Ngừng kinh doanh. | Login with account manager or eatery owner role. | Passed | 2024-04-02 | LongCH | Passed | 2024-04-06 | LongCH | Passed | 2024-04-10 | LongCH
Manager Product_5 | Test create product with Danh mục , Tên sản phẩm, Trạng thái,Giá ,Ảnh empty | 1. Click on "Sản phẩm" button on left-corner menu. 3. Click button "Thêm mới" 5. Enter input : - Danh mục : - Tên sản phẩm: - Giá : - Trạng thái : - Ảnh : 6. Click "Lưu". | 2. Product list screen is displayed. 4. Create product pop-up is display. 7. Fields "Danh mục", "Tên sản phẩm", "Giá", "Ảnh" will appear with red ticks and the mock-up "Thêm mới" is still display. | Login with account manager or eatery owner role. | Failed | 2024-04-02 | LongCH | Passed | 2024-04-06 | LongCH | Passed | 2024-04-10 | LongCH
Manager Product_6 | Test create product with "Tên sản phẩm" : empty | 1. Click on "Sản phẩm" button on left-corner menu. 3. Click button "Thêm mới" 5. Enter input: -Danh mục:"Món ăn phụ" - Tên sản phẩm : - Giá : 25000 -Trạng thái : Đang kinh doanh - Ảnh : image.jpg 6. Click "Lưu". | 2. Product list screen is displayed with fields. 4. Create product pop-up is display. 7. Fields "Tên sản phẩm" will appear with red ticks and the mock-up "Thêm mới" is still display. | Login with account manager or eatery owner role. | Failed | 2024-04-02 | LongCH | Passed | 2024-04-06 | LongCH | Passed | 2024-04-10 | LongCH
Manager Product_7 | Test create product with "Giá" : empty | 1. Click on "Sản phẩm" button on left-corner menu. 3. Click button "Thêm mới" 5. Enter input: -Danh mục:"Món ăn phụ" - Tên sản phẩm : "Cơm tấm" - Giá : -Trạng thái : Đang kinh doanh - Ảnh : image.jpg 6. Click "Lưu". | 2. Product list screen is displayed with fields. 4. Create product pop-up is display. 7. Fields "Giá" will appear with red ticks and the mock-up "Thêm mới" is still display. | Login with account manager or eatery owner role. | Failed | 2024-04-02 | LongCH | Failed | 2024-04-06 | LongCH | Passed | 2024-04-10 | LongCH
Manager Product_8 | Test UI update product. | 1. Click on "Sản phẩm" button on left-corner menu. 3. Click icon update of product in each line. | 2. Product list screen is displayed. 4. Update product pop-up is displayed with fields "Danh mục" , "Tên sản phẩm", "Giá", "Trạng thái", "Ảnh" with data, button "Đóng" , "Lưu". | Login with account manager or eatery owner role. | Failed | 2024-04-02 | LongCH | Passed | 2024-04-06 | LongCH | Passed | 2024-04-10 | LongCH
Manager Product_9 | Test update product with change "Danh mục". | 1. Click on "Sản phẩm" button on left-corner in menu. 3. Click icon update of product in each line. 5. Change "Danh mục" of this product. 6. Click "Lưu". | 2. Product list screen is displayed. 4. Update product pop-up is displayed. 7. Pop-up "Cập nhập thành công" is display. | Login with account manager or eatery owner role. | Passed | 2024-04-02 | LongCH | Passed | 2024-04-06 | LongCH | Passed | 2024-04-10 | LongCH
Manager Product_10 | Test update product with change "Tên sản phẩm" | 1. Click on "Sản phẩm" button on left-corner in menu. 3. Click icon update of product in each line. 5. Change "Tên sản phẩm" of this product. 6. Click "Lưu". | 2. Product list screen is displayed. 4. Update product pop-up is displayed. 7. Pop-up "Cập nhập thành công" is display. | Login with account manager or eatery owner role. | Passed | 2024-04-02 | LongCH | Passed | 2024-04-06 | LongCH | Passed | 2024-04-10 | LongCH
Manager Product_11 | Test update product with change "Giá" is number | 1. Click on "Sản phẩm" button on left-corner in menu. 3. Click icon update of product in each line. 5. Change "Giá" of this product is number. 6. Click "Lưu". | 2. Product list screen is displayed. 4. Update product pop-up is displayed. 7. Pop-up "Cập nhập thành công" is display. | Login with account manager or eatery owner role. | Failed | 2024-04-02 | LongCH | Failed | 2024-04-06 | LongCH | Passed | 2024-04-10 | LongCH
Manage Product_12 | Test update product with change "Giá" is not number. | 1. Click on "Sản phẩm" button on left-corner in menu. 3. Click icon update of product in each line. 5. Change "Giá" of this product is "ABCCC". 6. Click "Lưu". | 2. Product list screen is displayed. 4. Update product pop-up is displayed. 7. Pop-up "Cập nhập thành công" is display. | Login with account manager or eatery owner role. | Failed | 2024-04-02 | LongCH | Failed | 2024-04-06 | LongCH | Passed | 2024-04-10 | LongCH

## Manage Category
Workflow | Manage Category
Test requirement | Manage Category
Number of TCs | 9
Status | Passed | Failed | Pending | N/A
Total | 9 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Manage Category
Manager Category_1 | Test view list category. | 1. Click on "Danh mục" button on left-corner menu. | 2. Category list screen is displayed with fields "Số thứ tự", "Tên danh mục" , "Trạng thái" , "Quản lý". | Login with account manager or eatery owner role. | Failed | 2024-04-02 | LongCH | Passed | 2024-04-06 | LongCH | Passed | 2024-04-10 | LongCH
Manager Category_2 | Test view UI of create category. | 1. Click on "Danh mục" button on left-corner menu. 3. Click button "Thêm mới". | 2. Category list screen is displayed. 4. Create category pop-up is display with fields "Danh mục", "Trạng thái" and button "Đóng", "Lưu". | Login with account manager or eatery owner role. | Passed | 2024-04-02 | LongCH | Passed | 2024-04-06 | LongCH | Passed | 2024-04-10 | LongCH
Manager Category_3 | Test create category successfully. | 1. Click on "Danh mục" button on left-corner menu. 3. Click button "Thêm mới". 5. Enter input: - Danh mục : Món ngọt - Trạng thái : Đang kinh doanh. 6. Click "Lưu". | 2. Category list screen is displayed. 4. Create category pop-up is displayed. 7. Pop-up "Thêm mới thành công" is displayed. | Login with account manager or eatery owner role. | Passed | 2024-04-02 | LongCH | Passed | 2024-04-06 | LongCH | Passed | 2024-04-10 | LongCH
Manager Category_4 | Test create category with no select "Trạng thái". | 1. Click on "Danh mục" button on left-corner menu. 3. Click button "Thêm mới". 5. Enter input: - Danh mục : Món mặn - Trạng thái : 6. Click "Lưu". | 2. Category list screen is displayed. 4. Create category pop-up is displayed. 7. Fields "Trạng thái" will appear with red ticks and the mock-up "Thêm mới" is still display. | Login with account manager or eatery owner role. | Failed | 2024-04-02 | LongCH | Failed | 2024-04-06 | LongCH | Passed | 2024-04-10 | LongCH
Manager Category_5 | Test create category with "Danh mục" is empty. | 1. Click on "Danh mục" button on left-corner menu. 3. Click button "Thêm mới". 5. Enter input: - Danh mục : - Trạng thái : Đang kinh doanh. 6. Click "Lưu". | 2. Category list screen is displayed. 4. Create category pop-up is displayed. 7. Fields "Danh mục" will appear with red ticks and the mock-up "Thêm mới" is still display. | Login with account manager or eatery owner role. | Failed | 2024-04-02 | LongCH | Failed | 2024-04-06 | LongCH | Passed | 2024-04-10 | LongCH
Manager Category_6 | Test UI update category. | 1. Click on "Danh mục" button on left-corner menu. 3. Click icon update in each line of category. | 2. Category list screen is displayed. 4. Update category pop-up is displayed with fields "Danh mục" , "Trạng thái" with data, button "Đóng" , "Lưu". | Login with account manager or eatery owner role. | Passed | 2024-04-02 | LongCH | Passed | 2024-04-06 | LongCH | Passed | 2024-04-10 | LongCH
Manager Category_7 | Test update category with change "Danh mục". | 1. Click on "Danh mục" button on left-corner menu. 3. Click icon update in each line of category. 5. Change "Danh mục" of this category. 6. Click "Lưu". | 2. Category list screen is displayed. 4. Update category pop-up is displayed. 7. Pop-up "Cập nhập thành công" is display and "Danh mục" of this category change. | Login with account manager or eatery owner role. | Passed | 2024-04-02 | LongCH | Passed | 2024-04-06 | LongCH | Passed | 2024-04-10 | LongCH
Manager Category_8 | Test update category with change "Trạng thái". | 1. Click on "Danh mục" button on left-corner menu. 3. Click icon update in each line of category. 5. Change "Trạng thái" of this category. 6. Click "Lưu". | 2. Category list screen is displayed. 4. Update category pop-up is displayed. 7. Pop-up "Cập nhập thành công" is display | Login with account manager or eatery owner role. | Failed | 2024-04-02 | LongCH | Failed | 2024-04-06 | LongCH | Passed | 2024-04-10 | LongCH
Manager Category_9 | Test view detail category. | 1. Click on "Danh mục" button on left-corner menu. 3. Click icon detail in each line of category. | 2. Category list screen is displayed. 4. View detail category pop-up is displayed with fields "Danh mục", "Trạng thái" with data. | Login with account manager or eatery owner role. | Failed | 2024-04-02 | LongCH | Failed | 2024-04-06 | LongCH | Passed | 2024-04-10 | LongCH

## Manager User
Workflow | Manage User
Test requirement | Manage User
Number of TCs | 10
Status | Passed | Failed | Pending | N/A
Total | 10 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Manage User
Manager User_1 | Test view list user. | 1. Click on "Nhân viên" button on left-corner menu. | 2. User list screen is displayed with fields "Số thứ tự", "Tên người dùng" , "Tên tài khoản" , "Email", "SĐT", "Vị trí","Quản lý". | Login with account manager or eatery owner role. | Failed | 2024-04-03 | LongCH | Failed | 2024-04-07 | LongCH | Passed | 2024-04-11 | LongCH
Manager User_2 | Test UI create user. | 1. Click on "Nhân viên" button on left-corner menu. 3. Click on "Thêm mới" button. | 2. User list screen is displayed. 4. The create pop-up will display with "Họ tên" , "Tài khoản" , "Số điện thoại", "Email" ,"Phân quyền". | Login with account manager or eatery owner role. | Failed | 2024-04-03 | LongCH | Passed | 2024-04-07 | LongCH | Passed | 2024-04-11 | LongCH
Manager User_3 | Test create user successfully. | 1. Click on "Nhân viên" button on left-corner menu. 3. Click on "Thêm mới" button. 5. Enter input : - Họ tên : nguyễn khánh - Tài khoản : khanh_2345 - Số điện thoại : 0978124523 - Email : khanh_3456@gmail.com - Phân quyền : Admin. 6. Click "Lưu". | 2. User list screen is displayed. 4. The create pop-up will display. 7. Pop-up is "Thành công" and the user is added to the user list. | Login with account manager or eatery owner role. | Passed | 2024-04-03 | LongCH | Passed | 2024-04-07 | LongCH | Passed | 2024-04-11 | LongCH
Manager User_4 | Test create user with blank "Họ tên" | 1. Click on "Nhân viên" button on left-corner menu. 3. Click on "Thêm mới" button. 5. Enter input: - Họ tên : - Tài khoản : huy_234598 - Số điện thoại : 0978147624 - Email : huy_343456@gmail.com - Phân quyền : Admin. 6. Click "Lưu". | 2. User list screen is displayed. 4. The create pop-up will display. 7. Fields "Họ tên" will appear with red ticks and the mock-up "Thêm mới" is still display. | Login with account manager or eatery owner role. | Failed | 2024-04-03 | LongCH | Passed | 2024-04-07 | LongCH | Passed | 2024-04-11 | LongCH
Manager User_5 | Test create user with "Họ tên" have one character | 1. Click on "Nhân viên" button on left-corner menu. 3. Click on "Thêm mới" button. 5. Enter input: - Họ tên : h - Tài khoản : huy_234598 - Số điện thoại : 0978147624 - Email : huy_343456@gmail.com - Phân quyền : Admin. 6. Click "Lưu". | 2. User list screen is displayed. 4. The create pop-up will display. 7. Fields "Họ tên" will appear with red ticks and the mock-up "Thêm mới" is still display. | Login with account manager or eatery owner role. | Passed | 2024-04-03 | LongCH | Passed | 2024-04-07 | LongCH | Passed | 2024-04-11 | LongCH
Manager User_6 | Test create user with blank "Tài khoản" | 1. Click on "Nhân viên" button on left-corner menu. 3. Click on "Thêm mới" button. 5. Enter input: - Họ tên : cao ha - Tài khoản : - Số điện thoại : 0978123435 - Email : hacao_234@gmail.com - Phân quyền : Chef. 6. Click "Lưu". | 2. User list screen is displayed. 4. The create pop-up will display. 7. Fields "Tài khoản" will appear with red ticks and the mock-up "Thêm mới" is still display. | Login with account manager or eatery owner role. | Failed | 2024-04-03 | LongCH | Failed | 2024-04-07 | LongCH | Passed | 2024-04-11 | LongCH
Manager User_7 | Test create user with blank "Số điện thoại" | 1. Click on "Nhân viên" button on left-corner menu. 3. Click on "Thêm mới" button. 5. Enter input: - Họ tên : cao ha - Tài khoản : hacao_456 - Số điện thoại : - Email : hacao_234@gmail.com - Phân quyền : Chef. 6. Click "Lưu". | 2. User list screen is displayed. 4. The create pop-up will display. 7. Fields "Số điện thoại" will appear with red ticks and the mock-up "Thêm mới" is still display. | Login with account manager or eatery owner role. | Failed | 2024-04-03 | LongCH | Failed | 2024-04-07 | LongCH | Passed | 2024-04-11 | LongCH
Manager User_8 | Test create user with "Số điện thoại" is not number. | 1. Click on "Nhân viên" button on left-corner menu. 3. Click on "Thêm mới" button. 5. Enter input: - Họ tên : nguyen huy - Tài khoản : huynguyen_789 - Số điện thoại : ABCCC - Email : huynguyen_789@gmail.com - Phân quyền : Waiter. 6. Click "Lưu". | 2. User list screen is displayed. 4. The create pop-up will display. 7. Fields "Số điện thoại" will appear with red ticks and the mock-up "Thêm mới" is still display. | Login with account manager or eatery owner role. | Passed | 2024-04-03 | LongCH | Passed | 2024-04-07 | LongCH | Passed | 2024-04-11 | LongCH
Manager User_9 | Test create user with "Số điện thoại" have 10 digits. | 1. Click on "Nhân viên" button on left-corner menu. 3. Click on "Thêm mới" button. 5. Enter input: - Họ tên : khanhvan - Tài khoản : khanhvan_123 - Số điện thoại : 0912345678 - Email : khanhvan_123@gmail.com - Phân quyền : Cashier 6. Click "Lưu". | 2. User list screen is displayed. 4. The create pop-up will display. 7. Pop-up is "Thành công" and the user is added to the user list. | Login with account manager or eatery owner role. | Passed | 2024-04-03 | LongCH | Passed | 2024-04-07 | LongCH | Passed | 2024-04-11 | LongCH
Manager User_10 | Test view detail user. | 1. Click on "Nhân viên" button on left-corner menu. 3. Click icon detail of each user. | 2. User list screen is displayed. 4. View detail user pop-up is displayed with fields "Họ tên", "Email", "Số điện thoại", "Tài khoản","Phân quyền" with data. | Login with account manager or eatery owner role. | Passed | 2024-04-03 | LongCH | Passed | 2024-04-07 | LongCH | Passed | 2024-04-11 | LongCH

## Manage Table
Workflow | Manage User
Test requirement | Manage User
Number of TCs | 8
Status | Passed | Failed | Pending | N/A
Total | 8 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Manager Table
Manager Table_1 | Test view list table. | 1. Click on "Quản lý bàn" button on left-corner menu. | 2. Table list for manager screen is displayed with "Số thứ tự", "Tên bàn","Vị trí","Trạng thái", "Quản lý" fields. | Login with account manager or eatery owner role. | Failed | 2024-04-03 | LongCH | Passed | 2024-04-07 | LongCH | Passed | 2024-04-11 | LongCH
Manager Table_2 | Test UI create table. | 1. Click on "Quản lý bàn" button on left-corner menu. 3. Click "Thêm mới" button. | 2. Table list for manager screen is displayed. 4. The create pop-up will display with "Tên bàn", "Vị trí", "Trạng thái" and "Lưu", "Đóng" button. | Login with account manager or eatery owner role. | Failed | 2024-04-03 | LongCH | Passed | 2024-04-07 | LongCH | Passed | 2024-04-11 | LongCH
Manager Table_3 | Test create table successfully. | 1. Click on "Quản lý bàn" button on left-corner menu. 3. Click "Thêm mới" button. 4. Enter input: - Tên bàn : Bàn 11 - Vị trí : Tầng 2 - Trạng thái : Trống 5. Click "Lưu". | 2. Table list for manager screen is displayed. 6. Pop-up is "Thêm mới thành công" and the table is added to the table list. | Login with account manager or eatery owner role. | Failed | 2024-04-03 | LongCH | Failed | 2024-04-07 | LongCH | Passed | 2024-04-11 | LongCH
Manager Table_4 | Test create table with blank "Tên bàn". | 1. Click on "Quản lý bàn" button on left-corner menu. 3. Click "Thêm mới" button. 4. Do not enter "Tên bàn". 5. Click "Lưu". | 2. Table list for manager screen is displayed. 6. Fields "Tên bàn" will appear with red ticks and the mock-up "Thêm mới" is still display. | Login with account manager or eatery owner role. | Passed | 2024-04-03 | LongCH | Passed | 2024-04-07 | LongCH | Passed | 2024-04-11 | LongCH
Manger Table_5 | Test create table with no select "Vị trí". | 1. Click on "Quản lý bàn" button on left-corner menu. 3. Click "Thêm mới" button. 4. Do not select "Vị trí" of table. 5. Click "Lưu". | 2. Table list for manager screen is displayed. 6. Fields "Vị trí" will appear with red ticks and the mock-up "Thêm mới" is still display. | Login with account manager or eatery owner role. | Failed | 2024-04-03 | LongCH | Failed | 2024-04-07 | LongCH | Passed | 2024-04-11 | LongCH
Manager Table_6 | Test UI update table | 1. Click on "Quản lý bàn" button on left-corner menu. 3. Click icon update of table in each line. | 2. Table list for manager screen is displayed. 4. The update table pop-up will display "Tên bàn" , "Vị trí" , "Trạng thái" and "Đóng" , "Lưu" button with data. | Login with account manager or eatery owner role. | Passed | 2024-04-03 | LongCH | Passed | 2024-04-07 | LongCH | Passed | 2024-04-11 | LongCH
Manager Table_7 | Test change name of table | 1. Click on "Quản lý bàn" button on left-corner menu. 3. Click icon update of table in each line. 5. Change name of this table. 6. Click "Lưu". | 2. Table list for manager screen is displayed. 4. The update table pop-up will display. 7. Pop-up "Sửa thành công" is display and name of this table will change. | Login with account manager or eatery owner role. | Failed | 2024-04-03 | LongCH | Failed | 2024-04-07 | LongCH | Passed | 2024-04-11 | LongCH
Manager Table_8 | Test change "Vị trí" of table. | 1. Click on "Quản lý bàn" button on left-corner menu. 3. Click icon update of table in each line. 5. Change "Vị trí" of this table. 6. Click "Lưu". | 2. Table list for manager screen is displayed. 4. The update table pop-up will display. 7. Pop-up "Sửa thành công" is display and name of this table will change. | Login with account manager or eatery owner role. | Failed | 2024-04-03 | LongCH | Failed | 2024-04-07 | LongCH | Passed | 2024-04-11 | LongCH

## Manage Cart
Workflow | Manage Cart
Test requirement | Manage Cart
Number of TCs | 7
Status | Passed | Failed | Pending | N/A
Total | 7 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Manager Cart
Manager Cart_1 | Test pop-up add product to cart. | 1. Click on "Bàn" button on menu. 3. Enter name of customer and click "Xác nhận". 5. Click product. | 2. Pop-up "Nhập tên khách hàng" is display. 4. Screen "Thực đơn" is displayed. 6. Pop-up "Thêm vào giỏ hàng" display with fileds "Tên sản phẩm", "Giá", "Số lượng","Ghi chú đơn hàng". | Login with account waiter. | Failed | 2024-04-04 | LongCH | Failed | 2024-04-08 | LongCH | Passed | 2024-04-12 | LongCH
Manager Cart_2 | Test add product to cart with number of product >0 | 1. Click on "Bàn" button on menu. 3. Enter name of customer and click "Xác nhận". 5. Click product. 7. Enter number of product > 0 | 2. Pop-up "Nhập tên khách hàng" is display. 4. Screen "Thực đơn" is displayed. 6. Pop-up "Thêm vào giỏ hàng" display. 7. Pop-up "Đã thêm vào giỏ hàng" display. | Login with account waiter. | Passed | 2024-04-04 | LongCH | Passed | 2024-04-08 | LongCH | Passed | 2024-04-12 | LongCH
Manager Cart_3 | Test add product to cart with number of product < 0 | 1. Click on "Bàn" button on menu. 3. Enter name of customer and click "Xác nhận". 5. Click product. 7. Enter number of product < 0 | 2. Pop-up "Nhập tên khách hàng" is display. 4. Screen "Thực đơn" is displayed. 6. Pop-up "Thêm vào giỏ hàng" display. 7. Pop-up "Thêm thất bại" display. | Login with account waiter. | Failed | 2024-04-04 | LongCH | Failed | 2024-04-08 | LongCH | Passed | 2024-04-12 | LongCH
Manager Cart_4 | Test add product to cart with enter quantity is not number. | 1. Click on "Bàn" button on menu. 3. Enter name of customer and click "Xác nhận". 5. Click product. 7. Enter number of product is "ABCC" | 2. Pop-up "Nhập tên khách hàng" is display. 4. Screen "Thực đơn" is displayed. 6. Pop-up "Thêm vào giỏ hàng" display. 7. ABCC" is not displayed in the quantity section. | Login with account waiter. | Failed | 2024-04-04 | LongCH | Passed | 2024-04-08 | LongCH | Passed | 2024-04-12 | LongCH
Manager Cart_5 | Test increase number of product in cart. | 1. Click on "Bàn" button on menu. 3. Enter name of customer and click "Xác nhận". 5. Choose produts and add to cart. 6. Click "Giỏ hàng". 8. Click button "+" of product. | 2. Pop-up "Nhập tên khách hàng" is display. 4. Screen "Thực đơn" is displayed. 7. "Giỏ hàng" is displayed. 9. The number of product is increases. | Login with account waiter. | Passed | 2024-04-04 | LongCH | Passed | 2024-04-08 | LongCH | Passed | 2024-04-12 | LongCH
Manager Cart_6 | Test reduce number of product in cart. | 1. Click on "Bàn" button on menu. 3. Enter name of customer and click "Xác nhận". 5. Choose produts and add to cart. 6. Click "Giỏ hàng". 8. Click button "-" of product. | 2. Pop-up "Nhập tên khách hàng" is display. 4. Screen "Thực đơn" is displayed. 7. "Giỏ hàng" is displayed. 9. The number of product is reduce. | Login with account waiter. | Failed | 2024-04-04 | LongCH | Passed | 2024-04-08 | LongCH | Passed | 2024-04-12 | LongCH
Manager Cart_7 | Test delete product in cart | 1. Click on "Bàn" button on menu. 3. Enter name of customer and click "Xác nhận". 5. Choose produts and add to cart. 6. Click "Giỏ hàng". 8. Click icon delete. | 2. Pop-up "Nhập tên khách hàng" is display. 4. Screen "Thực đơn" is displayed. 7. "Giỏ hàng" is displayed. 9. The product is disappear. | Login with account waiter. | Failed | 2024-04-04 | LongCH | Passed | 2024-04-08 | LongCH | Passed | 2024-04-12 | LongCH

## Manager Order
Workflow | Manage Order
Test requirement | Manage Order
Number of TCs | 2
Status | Passed | Failed | Pending | N/A
Total | 2 | 0 | 0 | 0
Test Case ID | Test Case Description | Test Case Procedure | Expected Results | Pre-conditions | Round 1 | Test date | Tester | Round 2 | Test date | Tester | Round 3 | Test date | Tester | Note
Manager Order
Manager Order_1 | Test view list order. | 1. Click on "Giao dịch" button on menu. | 2. The list order screen is display with "Số thứ tự", "Tên khách", "Tổng món" , "Tổng tiền" , "Tên bàn", "Quản lý" | Login with account manager or eatery owner. | Failed | 2024-04-04 | LongCH | Passed | 2024-04-08 | LongCH | Passed | 2024-04-12 | LongCH
Manager Order_2 | Test view order detail. | 1. Click on "Giao dịch" button on menu. 3. Click icon detail of order. | 2. The list order screen is display with "Số thứ tự", "Tên khách", "Tổng món" , "Tổng tiền" , "Tên bàn", "Quản lý". 4. Displays a list of available dishes with the quantities in this order. | Login with account manager or eatery owner. | Passed | 2024-04-04 | LongCH | Passed | 2024-04-08 | LongCH | Passed | 2024-04-12 | LongCH